## ELM-30-A
ELM TRADING & CONTRACTING WLL ONGOING PROJECTS BRIEF PROGRESS REPORTING NO-30-A | [9 empty] | Issue Date: 21 Feb 2021 Cut-off Date:18 Feb 2021 Rev: 00 |  |  |  | 2021-02-18
PROJECT SUMMARY |  | PROJECT METRICS |  |  |  |  | PROJECT SUMMARY |  | PROJECT METRICS | [8 empty] | % Progress Till Date
Project | Waldorf Astoria | Weekly Progress |  |  |  |  | Project | Qatar Petroleum District | Weekly Progress | [6 empty] | Amount | Wt% | Plan % | Actual % | WT% Plan | WT% Actual |  | Planned % | Actual % | WT% Plan | WT% Actual | Tasks
Client | La Jolla | Tasks | Planned | Actual | Variance | Wt% | Client | Qatar Petroleum | Tasks | Planned | Actual | Variance | Wt% |  | Prev Contract Sum | 6966200 | 68.86% | 61.5% | 60.5% | 42.35% | 41.66% |  | 0.5% | 0.5% | 0.3075% | 0.3025% | Engineering | 68.86% | 68.86% | 78.16% | 76.76%
Consultant | Lacasa Qatar | Engineering | 0% | 0% | 0% | 18.8% | Consultant | AEB | Engineering | 0% | 0.04281% | 0.04281% | 5% |  | Additional Contract Sum | 3150000 | 31.14% | 0% | 0% | 0% | 0% |  | 0.5% | 0.5% | 0.3075% | 0.3025% | Procurement | 68.86% | 68.86% | 76.21% | 75.27%
Main Contractor | Harinsa Con. Com. Qatar | Procurement | 0% | 0.06% | 0.06% | 44.2% | Main Contractor | Medgulf Construction | Procurement | 0% | 1.338% | 1.338% | 55% |  | TOTAL: | 10116200 | 100% | 61.5% | 60.5% | 42.35% | 41.66% |  | 2% | 2% | 1.23% | 1.21% | Construction | 31.68% | 28.92% | 34.95% | 32.32%
ELM Contract Type | Lump-Sum | Construction | 0% | 0.51% | 0.51% | 37% | ELM Contract Type | Lump-sum | Construction | 0% | 0.9732% | 0.9732% | 40% | [9 empty] | 0% | 0% | 0% | 0% | Desnagging | 0% | 0% | 0% | 0%
ELM Contract Sum | 115155404 | Desnagging | 0% | 0% | 0% | 0% | ELM Contract Sum | 7601956.65 | Desnagging | 0% | 0% | 0% | 0% | [9 empty] | 0.75% | 0.75% | 0.4612% | 0.4537% | Overall | 42.35% | 41.66% | 46.3% | 45.56%
ELM Approved Variations | 0 | Overall | 0% | 0.11% | 0.11% | 100% | ELM Approved Variations | 2514243.35 | Overall | 0% | 1.127% | 1.127% | 100% |  | 10116200 | Total Contract Sum to Date
ELM Revised Contract Sum | 115155404 | Cumulative Progress |  |  |  |  | ELM Revised Contract Sum | 10116200 | Cumulative Progress
ELM Submitted Variation Orders | 7576299.93 | Tasks | Planned | Actual | Variance | Wt% | ELM Submitted Variation Orders | 0 | Tasks | Planned | Actual | Variance | Wt% | [9 empty] | Planned % | Actual % | WT% Plan | WT% Actual | Tasks |  |  | 1.172% | 0.7676%
ELM Expected Variation Orders | 6617116 | Engineering | 100% | 82.18% | -17.82% | 18.8% | ELM Expected Variation Orders | 0 | Engineering | 100% | 84.74% | -15.26% | 5% |  | 8084801.6337 | CTC Estimated | [6 empty] | 100% | 100% | 68.86% | 68.86% | Engineering |  |  | 0.9526% | 0.7527%
ELM Forecasted Cost-to-Complete | 118651451.92 | Procurement | 100% | 61.81% | -38.19% | 44.2% | ELM Forecasted Cost-to-Complete | 8420922.08 | Procurement | 100% | 66.37% | -33.63% | 55% |  | 79.92% | CTC % | [6 empty] | 100% | 100% | 68.86% | 68.86% | Procurement |  |  | 0.4369% | 0.3232%
ELM Contract End Date | 2020-03-15 | Construction | 100% | 27.86% | -72.14% | 37% | ELM Contract End Date | 2020-06-30 | Construction | 100% | 39.15% | -60.85% | 40% | [9 empty] | 46% | 42% | 31.68% | 28.92% | Construction |  |  | 0% | 0%
ELM EOT | 382 | Desnagging | 100% | 0% | -100% | 0% | ELM EOT | 168 | Desnagging | 0% | 0% | 0% | 0% | [9 empty] | 0% | 0% | 0% | 0% | Desnagging |  |  | 0.463% | 0.4556%
ELM Contract Revised End Date | 2020-12-31 | Overall | 100% | 54.38% | -45.62% | 100% | ELM Contract Revised End Date | 2020-12-15 | Overall | 100% | 56.4% | -43.6% | 100% |  | Previous Manpower |  |  | WA |  |  |  | QPD | 61.5% | 60.5% | 42.35% | 41.66% | Overall
ELM Revised Baseline Programme | 2021-05-31 | Manpower (man x days) |  |  |  |  | ELM Revised Baseline Programme | 2020-12-15 | Manpower (man x days) | [5 empty] | Manpower (man x days) |  |  |  | Manpower (man x days) | [10 empty] | 79.33% | 77.53%
ELM Forecasted Completion Date | 2021-06-22 | ID | Indirect | Direct | Total |  | ELM Forecasted Completion Date | 2021-04-30 | ID | Indirect | Direct | Total |  |  | ID | Indirect | Direct | Total | ID | Indirect | Direct | Total | [7 empty] | 77.16% | 76.02%
EOT to be Raised | 173 | Weekly | 29 | 222 | 251 |  | EOT to be Raised | 136 | Weekly | 2 | 12 | 14 |  |  | Weekly | 29 | 185 | 214 | Weekly | 2 | 12 | 14 | [7 empty] | 35.39% | 32.64%
ELM Cost to Date (CTD) - 10/11/2020 | 46584556.03 | Cumulative | 11976 | 66444 | 78420 |  | ELM Cost to Date (CTD) - 10/11/2020 | 2992825.55 | Cumulative | 132 | 912 | 1044 |  |  | Cumulative | 11802 | 65112 | 76914 | Cumulative | 120 | 840 | 960 | [7 empty] | 0% | 0%
[30 empty] | 46.77% | 46.02%
OUTSTANDING ISSUES & AREAS OF CONCERN |  | COST & TIME INDICATORS |  |  |  |  | OUTSTANDING ISSUES & AREAS OF CONCERN |  | COST & TIME INDICATORS
1-) Extension of Time & Cost Claim Clarification |  | Project Duration |  | 748 |  |  | 1-) Logistic and Storage for Material Deliveries |  | Project Duration |  | 498
2-) Handing Over - Availability of Open Work Front for ELM to proceed |  | Time Elapsed |  | 645 |  |  | 2.) Handing Over of Area and Access Dates |  | Time Elapsed |  | 563
3-) MEP Clearances |  | Time Remaining |  | 103 |  |  | 3.) EOT to be raised - Workfront partially given for ELM |  | Time Remaining |  | -65
4-) Design Changes / Change in Material Specifications |  | Completion % (Time) |  | 86.23% |  |  | 3.) EOT to be raised - Until 30th April 2021 |  | Completion % (Time) |  | 100%
5-) Approvals of Eng. Submissions affecting Procurement & Deliveries |  | Approved Cumulative IPC |  | 56111211.3745 |  |  |  |  | Approved Cumulative IPC |  | 2473556.94
6-) Late Procurement/Fabrication and Deliveries due to late approvals |  | Remaing IPC |  | 59044192.6255 |  |  |  |  | Remaing IPC |  | 7642643.06
7-) Swimming pool MEP Clearance not yet finalised by HCCQ |  | Completion % (Cost) |  | 48.73% |  |  |  |  | Completion % (Cost) |  | 24.45%
PROJECT SUMMARY |  | PROJECT METRICS |  |  |  |  | PROJECT SUMMARY |  | PROJECT METRICS
Project | W Hotel SPA | Weekly Progress |  |  |  |  | Project | Aman Hospital Project | Weekly Progress
Client | Nozul Hotels & Resorts WLL | Tasks | Planned | Actual | Variance | Wt% | Client | Aman Hospital WLL | Tasks | Planned | Actual | Variance | Wt%
Consultant | Hotel Management | Engineering | 0% | 0% | 0% | 0% | Consultant | KEO | Engineering | 2.814% | 1.028% | -1.786% | 3.26%
Main Contractor | ELM Contracting | Procurement | 0% | 0.05% | 0.05% | 60% | Main Contractor | Medgulf Construction | Procurement | 1.814% | 1.793% | -0.02124% | 36.54%
ELM Contract Type | Lump-Sum | Construction | 0% | 0.05% | 0.05% | 40% | ELM Contract Type | Lump-sum | Construction | 2.131% | 0.7289% | -1.402% | 60.2%
ELM Contract Sum | 8354338 | Desnagging | 0% | 0% | 0% | 0% | ELM Contract Sum | 58213000 | Desnagging | 0% | 0% | 0% | 0%
ELM Approved Variations | 0 | Overall | 0% | 0.05% | 0.05% | 100% | ELM Approved Variations | 0 | Overall | 2.032% | 1.167% | -0.8652% | 100%
ELM Revised Contract Sum | 8354338 | Cumulative Progress |  |  |  |  | ELM Revised Contract Sum | 58213000 | Cumulative Progress
ELM Submitted Variation Orders | 0 | Tasks | Planned | Actual | Variance | Wt% | ELM Submitted Variation Orders | 0 | Tasks | Planned | Actual | Variance | Wt%
ELM Expected Variation Orders | 0 | Engineering | 100% | 100% | 0% | 0% | ELM Expected Variation Orders | -346353.72 | Engineering | 89.65% | 73.27% | -16.39% | 3.26%
ELM Forecasted Cost-to-Complete | 7716100 | Procurement | 100% | 100% | 0% | 60% | ELM Forecasted Cost-to-Complete | 53192052.21 | Procurement | 43.11% | 33.74% | -9.364% | 36.54%
ELM Contract End Date | 2020-07-01 | Construction | 100% | 99.98% | -0.015% | 40% | ELM Contract End Date | 2021-02-10 | Construction | 20.66% | 20.96% | 0.2967% | 60.2%
ELM EOT | 0 | Desnagging | 0% | 0% | 0% | 0% | ELM EOT | 0 | Desnagging | 0% | 0% | 0% | 0% | [9 empty] | Note:
ELM Contract Revised End Date | 2020-11-15 | Overall | 100% | 99.99% | -0.006% | 100% | ELM Contract Revised End Date | 2021-02-10 | Overall | 32.5% | 28.24% | -4.263% | 100% |  | Previous Manpower |  |  | W |  |  |  | AH | Changed As per Overall Preoject Rev. BL
ELM Revised Baseline Programme | 2020-11-15 | Manpower (man x days) |  |  |  |  | ELM Revised Baseline Programme | 2021-06-15 | Manpower (man x days) | [5 empty] | Manpower (man x days) |  |  |  | Manpower (man x days) |  |  |  | Not as per Mitigation
ELM Forecasted Completion Date | 2021-02-04 | ID | Indirect | Direct | Total |  | ELM Forecasted Completion Date | 2021-06-21 | ID | Indirect | Direct | Total |  |  | ID | Indirect | Direct | Total | ID | Indirect | Direct | Total
EOT to be Raised | 81 | Weekly | 2 | 5 | 7 |  | EOT to be Raised | 131 | Weekly | 35 | 266 | 301 |  |  | Weekly | 2 | 5 | 7 | Weekly | 32 | 282 | 314
ELM Cost to Date (CTD) - 10/11/2020 | 7303519.36 | Cumulative | 894 | 15672 | 16566 |  | ELM Cost to Date (CTD) - 10/11/2020 | 3985797.1 | Cumulative | 5622 | 23202 | 28824 |  |  | Cumulative | 882 | 15642 | 16524 | Cumulative | 5412 | 21606 | 27018
OUTSTANDING ISSUES & AREAS OF CONCERN |  | COST & TIME INDICATORS |  |  |  |  | OUTSTANDING ISSUES & AREAS OF CONCERN |  | COST & TIME INDICATORS
1-) Final touch up work |  | Project Duration |  | 401 |  |  | 1-) New Introduced Target Dates (OTS-02) vs. Actual (EOT to be raised) |  | Project Duration |  | 402
2-) Inspection and handing over remaining |  | Time Elapsed |  | 415 |  |  | 2-) Value Engineering Materials Approvals & Confimation by KEO/TAHPI |  | Time Elapsed |  | 284
3-) Remaining Testing of Functionality of devices |  | Time Remaining |  | -14 |  |  | 3-) Long Lead Items Delivery |  | Time Remaining |  | 118
4-) Final Cleaning |  | Completion % (Time) |  | 100% |  |  | 4-) Action Plan for Delayed Engineering & Procurement Works due to approvals |  | Completion % (Time) |  | 70.65%
5-) …………… |  | Approved Cumulative IPC |  | 7150241.85 |  |  | 5-) Remaining Civil & MEP Works at Wet Areas by others |  | Approved Cumulative IPC |  | 3818011.54
6-) …………… |  | Remaing IPC |  | 1204096.15 |  |  | 6-) Data is Referred from New OTS-2 Schedule introduced by MG for reporting |  | Remaing IPC |  | 54394988.46
7-) …………… |  | Completion % (Cost) |  | 85.59% |  |  |  |  | Completion % (Cost) |  | 6.559%
Formulas:
Qatar Petroleum District = M16+[Qatar Petroleum District, row above]

## Progress Photos-30-A
ELM TRADING & CONTRACTING WLL ONGOING PROJECTS BRIEF PROGRESS REPORTING NO30-A - SITE PHOTOS |  | Issue Date: 21 Feb 2021 Cut-off Date:18 Feb 2021 Rev: 00
WALDORF ASTORIA PROJECT | QATAR PETROLEUM DISTRICT PROJECT
Various Progress (Fit-Out) Installation Works
W HOTEL SPA PROJECT | AMAN HOSPITAL PROJECT
Various Progress on Fit-Out Finishes Final Touch Up Works | Dry Wall Patition Works & Mock-up Installation
Hand Over Stage

## ELM-30-B
ELM TRADING & CONTRACTING WLL ONGOING PROJECTS BRIEF PROGRESS REPORTING NO-30-B | [9 empty] | Issue Date: 21 Feb 2021 Cut-off Date:18 Feb 2021 Rev: 00 |  |  |  | 2021-02-18
PROJECT SUMMARY |  | PROJECT METRICS |  |  |  |  | PROJECT SUMMARY |  | PROJECT METRICS
Project | W Hotel Coya Restaurant | Weekly Progress |  |  |  |  | Project | Papillon Jewellry | Weekly Progress
Client | Nozul Hotels & Resorts WLL | Tasks | Planned | Actual | Variance | W% | Client | Papillon Jewellry LLC | Tasks | Planned | Actual | Variance | Wt%
Consultant | Hotel Management | Engineering | 0% | 0% | 0% | 5% | Consultant | - | Engineering | 0% | 0.15% | 0% | 10.65%
Main Contractor | ELM Contracting | Procurement | 0% | 1% | 1% | 55% | Main Contractor | ELM Contracting | Procurement | 1.5% | 0.25% | 0% | 53.61%
ELM Contract Type | Lump-Sum | Construction | 0% | 2.25% | 2.25% | 40% | ELM Contract Type | Lump-sum | Construction | 2.5% | 0% | 0% | 35.74%
ELM Contract Sum | 6250000 | Desnagging | 0% | 0% | 0% | 0% | ELM Contract Sum | 1282205 | Desnagging | 0% | 0% | 0% | 0%
ELM Approved Variations | 724228 | Overall | 0% | 1.45% | 1.45% | 100% | ELM Approved Variations | 0 | Overall | 1.698% | 0.15% | -1.548% | 100%
ELM Revised Contract Sum | 6974228 | Cumulative Progress |  |  |  |  | ELM Revised Contract Sum | 1282205 | Cumulative Progress
ELM Submitted Variation Orders | 0 | Tasks | Planned | Actual | Variance | W% | ELM Submitted Variation Orders | 0 | Tasks | Planned | Actual | Variance | Wt%
ELM Expected Variation Orders | 571123.79 | Engineering | 100% | 100% | 0% | 5% | ELM Expected Variation Orders | 0 | Engineering | 100% | 31.65% | 0% | 10.65%
ELM Forecasted Cost-to-Complete | 6262000 | Procurement | 100% | 100% | 0% | 55% | ELM Forecasted Cost-to-Complete | 1172088.2 | Procurement | 84.95% | 11.75% | 0% | 53.61%
ELM Contract End Date | 2020-11-15 | Construction | 100% | 97.25% | -2.75% | 40% | ELM Contract End Date | 2021-04-01 | Construction | 66.14% | 0% | 0% | 35.74%
ELM EOT | 0 | Desnagging | 100% | 0% | -100% | 0% | ELM EOT | 0 | Desnagging | 0% | 0% | 0% | 0%
ELM Contract Revised End Date | 2020-12-15 | Overall | 100% | 98.9% | -1.1% | 100% | ELM Contract Revised End Date | 2021-04-01 | Overall | 79.83% | 9.671% | -70.16% | 100% |  | Previous Manpower |  |  | WA |  |  |  | QPD
ELM Revised Baseline Programme | 2020-12-15 | Manpower (man x days) |  |  |  |  | ELM Revised Baseline Programme | 2021-04-01 | Manpower (man x days) | [5 empty] | Manpower (man x days) |  |  |  | Manpower (man x days)
ELM Forecasted Completion Date | 2021-02-10 | ID | Indirect | Direct | Total |  | ELM Forecasted Completion Date | 2021-04-01 | ID | Indirect | Direct | Total |  |  | ID | Indirect | Direct | Total | ID | Indirect | Direct | Total
EOT to be Raised | 57 | Weekly | 3 | 57 | 60 |  | EOT to be Raised | 0 | Weekly | 5 | 0 | 5 |  |  | Weekly | 3 | 57 | 60 | Weekly | 5 | 0 | 5
ELM Cost to Date (CTD) - 10/11/2020 | 1719925.97 | Cumulative | 108 | 2316 | 2424 |  | ELM Cost to Date (CTD) - 10/11/2020 | 122950 | Cumulative | 750 | 0 | 750 |  |  | Cumulative | 90 | 1974 | 2064 | Cumulative | 720 | 0 | 720
OUTSTANDING ISSUES & AREAS OF CONCERN |  | COST & TIME INDICATORS |  |  |  |  | OUTSTANDING ISSUES & AREAS OF CONCERN |  | COST & TIME INDICATORS
1-) Handing Over Stage |  | Project Duration |  | 203 |  |  | 1-) Project is Design & Build Work Scope by ELM |  | Project Duration |  | 243
2-) |  | Time Elapsed |  | 211 |  |  | 2-) Civil & Architectural Works design Pending Authority Approval |  | Time Elapsed |  | 201
3-) |  | Time Remaining |  | -8 |  |  | 3-) MEP Services design under finalization |  | Time Remaining |  | 42
4-) |  | Completion % (Time) |  | 100% |  |  | 4-) Building Permit not yet obtained and issued to start work. |  | Completion % (Time) |  | 82.72%
5-) |  | Approved Cumulative IPC |  | 2217881.5 |  |  | 5-) Design Finalization and IFC to be issued after Municipality Approval |  | Approved Cumulative IPC |  | 0
6-) |  | Remaing IPC |  | 4756346.5 |  |  | 6-) DC-1 Approval On-HOLD |  | Remaing IPC |  | 1282205
7-) |  | Completion % (Cost) |  | 31.8% |  |  |  |  | Completion % (Cost) |  | 0%
PROJECT SUMMARY |  | PROJECT METRICS |  |  |  |  | PROJECT SUMMARY |  | PROJECT METRICS
Project |  | Weekly Progress |  |  |  |  | Project |  | Weekly Progress
Client |  | Tasks | Planned | Actual | Variance | W% | Client |  | Tasks | Planned | Actual | Variance | W%
Consultant |  | Engineering |  |  |  |  | Consultant |  | Engineering
Main Contractor |  | Procurement |  |  |  |  | Main Contractor |  | Procurement
ELM Contract Type |  | Construction |  |  |  |  | ELM Contract Type |  | Construction
ELM Contract Sum |  | Desnagging |  |  |  |  | ELM Contract Sum |  | Desnagging
ELM Approved Variations |  | Overall |  |  |  |  | ELM Approved Variations |  | Overall
ELM Revised Contract Sum |  | Cumulative Progress |  |  |  |  | ELM Revised Contract Sum |  | Cumulative Progress
ELM Submitted Variation Orders |  | Tasks | Planned | Actual | Variance | W% | ELM Submitted Variation Orders |  | Tasks | Planned | Actual | Variance | W%
ELM Expected Variation Orders |  | Engineering |  |  |  |  | ELM Expected Variation Orders |  | Engineering
ELM Forecasted Cost-to-Complete |  | Procurement |  |  |  |  | ELM Forecasted Cost-to-Complete |  | Procurement
ELM Contract End Date |  | Construction |  |  |  |  | ELM Contract End Date |  | Construction
ELM EOT |  | Desnagging |  |  |  |  | ELM EOT |  | Desnagging
ELM Contract Revised End Date |  | Overall |  |  |  |  | ELM Contract Revised End Date |  | Overall | [5 empty] | Previous Manpower |  |  | W |  |  |  | AH
ELM Revised Baseline Programme |  | Manpower (man x days) |  |  |  |  | ELM Revised Baseline Programme |  | Manpower (man x days) | [5 empty] | Manpower (man x days) |  |  |  | Manpower (man x days)
ELM Forecasted Completion Date |  | ID | Indirect | Direct | Total |  | ELM Forecasted Completion Date |  | ID | Indirect | Direct | Total |  |  | ID | Indirect | Direct | Total | ID | Indirect | Direct | Total
EOT to be Raised |  | Weekly |  |  |  |  | EOT to be Raised |  | Weekly | [5 empty] | Weekly | 4 | 81 | 85 | Weekly | 28 | 98 | 126
ELM Cost to Date (CTD) |  | Cumulative |  |  |  |  | ELM Cost to Date (CTD) |  | Cumulative | [5 empty] | Cumulative | 672 | 14166 | 14838 | Cumulative | 2814 | 4362 | 7176
OUTSTANDING ISSUES & AREAS OF CONCERN |  | COST & TIME INDICATORS |  |  |  |  | OUTSTANDING ISSUES & AREAS OF CONCERN |  | COST & TIME INDICATORS
|  | Project Duration | [6 empty] | Project Duration
|  | Time Elapsed | [6 empty] | Time Elapsed
|  | Time Remaining | [6 empty] | Time Remaining
|  | Completion % (Time) | [6 empty] | Completion % (Time)
|  | Approved Cumulative IPC | [6 empty] | Approved Cumulative IPC
|  | Remaing IPC | [6 empty] | Remaing IPC
|  | Completion % (Cost) | [6 empty] | Completion % (Cost)
Formulas:
Papillon Jewellry = M16+[Papillon Jewellry, row above]

## Progress Photos-30-B
ELM TRADING & CONTRACTING WLL ONGOING PROJECTS BRIEF PROGRESS REPORTING NO-30-B - SITE PHOTOS |  | Issue Date: 21 Feb 2021 Cut-off Date:18 Feb 2021 Rev: 00
W HOTEL COYA RESTAURANT | PAPILLON JEWELLRY
Various Floor, Wall, Ceiling Finishing & Joineries | DESIGN CONCEPT ONLY (DESIGN & AUTHORITY APPROVAL STAGE)
Hand Over Stage

## Orig Contractual Dates (hidden)
Project | Waldorf Astoria |  | Project | Qatar Petroleum District | [5 empty] | Forecasted Completion |  |  |  | QPD
ELM Contract Start Date | 2019-05-16 |  | ELM Contract Start Date | 2019-08-05 | days | Mos. |  |  |  | days | Mos. | Working days
ELM Contract End Date | 2020-05-15 |  | ELM Contract End Date (new) | 2020-12-31 | 515 | 17.1667 |  |  |  | 236.2562 | 7.8752 | 204.7554 | Approx. 5+ months
EOT Completion Date | 2021-05-31 |  | EOT Completion Date | 30th April 2021 |  | 54.12% | completed | 45.88% | Remaining
Project | W Hotel Spa |  | Project | Aman Hospital Project | [5 empty] | Forecasted Completion |  |  |  | W-Hotel
ELM Contract Start Date | 2020-01-01 |  | ELM Contract Start Date | 2020-05-10 | days | Mos. |  |  |  | days | Mos. | Working days
ELM Contract End Date | 2020-06-30 |  | ELM Contract End Date | 2021-06-15 | 182 | 6.0667 |  |  |  | 0.01092 | 0.000364 | 0.009464 | Approx.2+ months
EOT Completion Date | 2021-02-04 |  | EOT Completion Date | TBC |  | 99.99% | completed | 0.006% | Remaining
to be raised
| 401 |  |  | 402 | [5 empty] | Cut-off: | 2021-02-18
| 366 | WA
382
Project | W Hotel Coya |  | Project | Papillon Jewellry
ELM Contract Start Date | 2020-07-22 |  | ELM Contract Start Date | 2020-08-01
ELM Contract End Date | 2020-12-15 |  | ELM Contract End Date | 2021-04-01
EOT Completion Date | 2020-12-15 |  | EOT Completion Date | TBC
2021-02-10
203
218
2021-02-25
1.0739
Formulas:
Waldorf Astoria = [Waldorf Astoria, row above]
Note on F4: Author: 7/30/2020 prev end date
Note on C17: Forecasted

## CTC Calculation (hidden)
Waldorf Astoria |  |  | Remarks
CTC |  | 97222334
% Progress | 54.38% | 52869505.2292
Less:
% Remaining | 45.62% | 44352828.7708 | estimated remaining expenses cost
QPD
CTC |  | 5567342
% Progress | 56.4% | 3140164.8114
Less:
% Remaining | 43.6% | 2427177.1886 | estimated remaining expenses cost