## Dashboard
|  |  |  | E. Prequalification Status | I. Manpower Status
Dashboard Report Date:
2018-05-28
A. Project Information
Project Code: | P069
Project Name: | Al Wukair Villa
Project Description: | Main Villa + Majilis + Clubhouse + Service Blocks + Ext. Works
Client: | Sheikh Mohammed Abdulrahman
Project Manager: | Engr. Ahmed Mohammed
Consultant: | VGC
Contract Award On: | 2017-05-18
Original Duration: | 532
Commencement Date: | 2017-08-01
Completion Date: | 2019-01-14
Revised Completion Date: | 2019-01-14
Project Value, Qar: | 23675265
Project Performance Index: | 0.57937
Project Status (Ahead/Delay): | -201 |  |  | F. Shop Drawing Status | J. Current % Progress Vs Previous % Progress
Forecasted Completion Date: | 2019-08-03 | [9 empty] | Previous % Progress
B. Project Duration Status | [10 empty] | Date | 2018-04-01
[11 empty] | Plan | 13.82%
[11 empty] | Actual | 4.013%
[11 empty] | Variance | -9.808%
[11 empty] | Progress | Loss
[11 empty] | SPI | 0.54672
Current % Progress
[11 empty] | Date | 2018-05-01
[11 empty] | Plan | 5.655%
C. Project Scope Progress Status | [10 empty] | Actual | 5.655%
[11 empty] | Variance | -1.11e-14%
[11 empty] | Progress | Gain
[11 empty] | SPI | 0.57937
|  |  |  | G. Materials Status | K. Project Cost Progress Status (S-Curve)
`
D. Look Ahead Scope Progress - Planned Vs Anticipated Actual
|  |  |  | H. Procurement Status | L. Project Financial Summary
[10 empty] | Until The Month Of |  | Remarks
[5 empty] | Original Contract Sum |  | Qar | 23675265 |  |  |  | Awarded
[5 empty] | Advance Payment |  | Qar | 3551289.75 |  |  |  | Invoiced
[5 empty] | Cum. Payment Applied |  | Qar | 9429099.87 |  | April | 2018 | Invoiced | 9429099.87
[5 empty] | Cum. Payment Received |  | Qar | 9429099.87 |  | April | 2018 | Payment TBC
[5 empty] | Cum. Payment Pending |  | Qar | 10768002.0659 |  | May | 2018 | Forecast For IPA003 | 10768002.0659
[5 empty] | Expected Next Payment |  | Qar
[5 empty] | M. Variation Orders & Claims | [7 empty] | 5.655%
[5 empty] | VO No. | Description |  |  |  | Amount in Qar |  | Status
[5 empty] | 1 | None To date
2
3
4
5
[9 empty] | Total | 0
|  | Next 2Weeks | 2.314%
|  | Next 4Weeks | 4.627%
Target%=4.63
Total:116

## A
Dashboard Report Date:
2018-05-28
A. Project Information
Project Code: | P069
Project Name: | Al Wukair Villa
Project Description: | Main Villa + Majilis + Clubhouse + Service Blocks + Ext. Works
Client: | Sheikh Mohammed Abdulrahman
Project Manager | Engr. Ahmed Mohammed
Consultant: | VGC
Contract Award On: | 2017-05-18
Original Duration: | 532
Commencement Date: | 2017-08-01
Completion Date: | 2019-01-14
Revised Completion Date: | 2019-01-14
Project Value, Qar: | 23675265
Project Performance Index: | 0.57937
Project Status (Ahead/Delay): | -201
Forecasted Completion Date: | 2019-08-03

## B
Duration Status
Total Duration | 532
Time Elapsed in Days | 301
Time Remaining in Days | 231
Time Elapsed in % | 56.58%
Time Remaining in % | 43.42%

## C
Project Scope Progress Status | %Planned | %Actual | % Variance | %Planned | %Actual | % Variance
Overall Project % Progress | 78.5% | 45.48% | -33.02% | 78.5% | 45.48% | -33.02%
PRELIMINARIES | 67.45% | 67.45% | 0%
ENABLING WORKS | 100% | 99.06% | -0.9405%
CIVIL AND STRUCTURAL WORKS | 90% | 77.97% | -12.03%
MEP WORKS | 13.5% | 8.067% | -5.433%
THERMAL AND MOISTURE PROTECTION | 0% | 0% | 0%
EXTERNAL CIVIL WORKS | 0% | 0% | 0%
SPECIALTIES | 0% | 0% | 0%
PROVISIONAL SUM | 0% | 0% | 0%

## D
| CURRENT |  |  |  | NEXT 2 WEEKS |  |  |  |  | NEXT Month
Project Scope Progress Status | %Planned | %Actual | % Variance | Project Scope Progress Status | %Planned | 2Wk Forecast | % Variance |  | Project Scope Progress Status | %Planned | 4Wk Forecast | % Variance
Overall Project % Progress | 78.5% | 45.48% | -33.02% | Overall Project % Progress | 80.82% | 47.8% | -33.02% | 2.314% | Overall Project % Progress (Forecast) | 83.13% | 50.11% | -33.02% | 4.627%
PRELIMINARIES | 67.45% | 67.45% | 0% | PRELIMINARIES | 67.92% | 67.59% | -0.3346% |  | PRELIMINARIES | 68.39% | 67.73% | -0.6692%
ENABLING WORKS | 100% | 99.06% | -0.9405% | ENABLING WORKS | 100% | 99.06% | -0.9462% |  | ENABLING WORKS | 100% | 99.06% | -0.9518%
CIVIL AND STRUCTURAL WORKS | 90% | 77.97% | -12.03% | CIVIL AND STRUCTURAL WORKS | 92.18% | 78.61% | -13.57% |  | CIVIL AND STRUCTURAL WORKS | 94.36% | 79.24% | -15.12%
MEP WORKS | 13.5% | 8.067% | -5.433% | MEP WORKS | 16.5% | 8.936% | -7.559% |  | MEP WORKS | 19.49% | 9.806% | -9.685%
THERMAL AND MOISTURE PROTECTION | 0% | 0% | 0% | THERMAL AND MOISTURE PROTECTION | 0% | 0% | 0% |  | THERMAL AND MOISTURE PROTECTION | 0% | 0% | 0%
EXTERNAL CIVIL WORKS | 0% | 0% | 0% | EXTERNAL CIVIL WORKS | 0% | 0% | 0% |  | EXTERNAL CIVIL WORKS | 0% | 0% | 0%
SPECIALTIES | 0% | 0% | 0% | SPECIALTIES | 0% | 0% | 0% |  | SPECIALTIES | 0% | 0% | 0%
PROVISIONAL SUM | 0% | 0% | 0% | PROVISIONAL SUM | 0% | 0% | 0% |  | PROVISIONAL SUM | 0% | 0% | 0%
Current |  |  |  |  | Next 2-Weeks | [6 empty] | Next 4-Weeks

## E
Prequalification
| Plan to Submit | Submitted | %Approved | %Variance | Total Submittals | Plan to Submit | Submitted | Approved
Civil/Structural | 100% | 100% | 100% | 0% | 18 | 18 | 18 | 18
Arch. (Excl. ID Fit-Out) | 100% | 0% | 0% | -100% | 1 | 1 | 0 | 0
Mechanical | 100% | 100% | 93.85% | 0% | 65 | 65 | 65 | 61
Electrical | 100% | 100% | 85.71% | 0% | 28 | 28 | 28 | 24
ELV | 100% | 100% | 0% | 0% | 4 | 4 | 4 | 0
[5 empty] | 116 | 116 | 115 | 103 | 12

## F
Shop Drawings
| Plan to Submit | Submitted | %Approved | %Variance | Total Submittals | Plan to Submit | Submitted | Approved
ARCH | 100% | 83.95% | 76.54% | -16.05% | 81 | 81 | 68 | 62
ARCH. GENERAL SITE DEVELOPMENT | 100% | 50% | 25% | -50% | 4 | 4 | 2 | 1
ELECTRICAL | 100% | 80.7% | 77.19% | -19.3% | 57 | 57 | 46 | 44
ELECTRICAL-ELV | 100% | 80.56% | 80.56% | -19.44% | 36 | 36 | 29 | 29
MECH | 100% | 44.83% | 33.33% | -55.17% | 87 | 87 | 39 | 29
SPECIALIST | 100% | 100% | 100% | 0% | 2 | 2 | 2 | 2
STRUCTURAL | 100% | 98.18% | 98.18% | -1.818% | 55 | 55 | 54 | 54
STRUCTURAL-GENERAL AND ENABLING | 100% | 100% | 100% | 0% | 9 | 9 | 9 | 9
[5 empty] | 331 | 331 | 249 | 230 | 19 | open

## G
Materials
| Plan to Submit | Submitted | %Approved | %Variance | Total Submittals | Plan to Submit | Submitted | Approved
BY SPECIALIST | 100% | 50% | 37.5% | -50% | 8 | 8 | 4 | 3
Civil/ Struct. | 100% | 47.37% | 47.37% | -52.63% | 19 | 19 | 9 | 9
DRAINAGE | 100% | 71.43% | 64.29% | -28.57% | 14 | 14 | 10 | 9
FIREFIGHTING | 100% | 0% | 0% | -100% | 1 | 1 | 0 | 0
HVAC | 100% | 68.18% | 68.18% | -31.82% | 22 | 22 | 15 | 15
PLUMBING | 100% | 90.91% | 72.73% | -9.091% | 22 | 22 | 20 | 16
ELECTRICAL | 100% | 42.31% | 42.31% | -57.69% | 26 | 26 | 11 | 11
[5 empty] | 112 | 112 | 69 | 63

## H
Procurement
| Plan to Procure | Procured | Delivered | %Variance | Total Procurement | Plan to Procure | Procured | Delivered
Civil | 100% | 76.92% | 76.92% | -23.08% | 13 | 13 | 10 | 10
Architectural (Excl. ID) | 100% | 100% | 100% | 0% | 5 | 5 | 5 | 5
Mechanical - HVAC | 100% | 28.57% | 28.57% | -71.43% | 42 | 42 | 12 | 12
Electrical | 100% | 45% | 45% | -55% | 20 | 20 | 9 | 9
ELV | 100% | 0% | 0% | -100% | 19 | 19 | 0 | 0
Specialties | 100% | 0% | 0% | -100% | 5 | 5 | 0 | 0
ID / Fit-out | 100% | 0% | 0% | -100% | 1 | 1 | 0 | 0
Landscape | 100% | 0% | 0% | -100% | 1 | 1 | 0 | 0
Façade | 100% | 0% | 0% | -100% | 1 | 1 | 0 | 0
[5 empty] | 107 | 107 | 36 | 36 | 71
71
[7 empty] | 33.64% | efficiency

## I.
AL WUKAIR VILLA
MANPOWER RESOURCE REQUIREMENT
Deisignation | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01
Helpers / Logistics | 55 | 95 | 99 | 99 | 95 | 99 | 95 | 99 | 99 | 88 | 99 | 95 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
Carpenter | 48 | 84 | 87 | 87 | 84 | 87 | 84 | 87 | 87 | 77 | 87 | 84 | 84 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Steelfixer | 54 | 95 | 98 | 98 | 95 | 98 | 95 | 98 | 98 | 87 | 98 | 95 | 94 | 94 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Concrete Mason | 18 | 32 | 33 | 33 | 32 | 33 | 32 | 33 | 33 | 29 | 33 | 32 | 32 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mechanical Workers | 6 | 9 | 10 | 10 | 9 | 10 | 9 | 10 | 10 | 9 | 10 | 9 | 228 | 228 | 228 | 228 | 228 | 228 | 228 | 54 | 54 | 54 | 0 | 0
Electrical Workers | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 10 | 10 | 57 | 57 | 57 | 57 | 57 | 57 | 57 | 0 | 0 | 0 | 0 | 0
ELV Installers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 41 | 41 | 0 | 0 | 0
Total Manpower | 187 | 325 | 337 | 337 | 325 | 337 | 325 | 337 | 337 | 299 | 337 | 325 | 540 | 540 | 540 | 330 | 330 | 330 | 371 | 140 | 140 | 99 | 45 | 45
Deisignation | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01
Planned Manpower | 187 | 325 | 337 | 337 | 325 | 337 | 325 | 337 | 337 | 299 | 337 | 325 | 540 | 540 | 540 | 330 | 330 | 330 | 371 | 140 | 140 | 99 | 45 | 45
Actual Manpower | 2017-05-01: 131; 2017-06-01: 228; 2017-07-01: 236; 2017-08-01: 236; 2017-09-01: 228; 2017-10-01: 236; 2017-11-01: 228; 2017-12-01: 236; 2018-01-01: 236; 2018-02-01: 210; 2018-03-01: 236; 2018-04-01: 228; 2018-05-01: 378
Cum. Monthly Planned Manpower | 187 | 512 | 849 | 1186 | 1511 | 1848 | 2173 | 2510 | 2847 | 3146 | 3483 | 3808 | 4348 | 4888 | 5428 | 5758 | 6088 | 6418 | 6789 | 6929 | 7069 | 7168 | 7213 | 7258
Cum. Monthly Actual Manpower | 2017-05-01: 187; 2017-06-01: 415; 2017-07-01: 651; 2017-08-01: 887; 2017-09-01: 1115; 2017-10-01: 1351; 2017-11-01: 1579; 2017-12-01: 1815; 2018-01-01: 2051; 2018-02-01: 2261; 2018-03-01: 2497; 2018-04-01: 2725; 2018-05-01: 3103
Deisignation | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01
Helpers / Logistics | 39 | 67 | 69 | 69 | 67 | 69 | 67 | 69 | 69 | 62 | 69 | 67 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
Carpenter | 34 | 59 | 61 | 61 | 59 | 61 | 59 | 61 | 61 | 54 | 61 | 59 | 59 | 59 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Steelfixer | 38 | 67 | 69 | 69 | 67 | 69 | 67 | 69 | 69 | 61 | 69 | 67 | 66 | 66 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Concrete Mason | 13 | 22 | 23 | 23 | 22 | 23 | 22 | 23 | 23 | 20 | 23 | 22 | 22 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mechanical Workers | 4 | 6 | 7 | 7 | 6 | 7 | 6 | 7 | 7 | 6 | 7 | 6 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 38 | 38 | 38 | 0 | 0
Electrical Workers | 4 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 7 | 7 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0
ELV Installers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 29 | 0 | 0 | 0
Total Manpower | 132 | 228 | 236 | 236 | 228 | 236 | 228 | 236 | 236 | 209 | 236 | 228 | 379 | 379 | 379 | 232 | 232 | 232 | 261 | 99 | 99 | 70 | 32 | 32
Deisignation | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01
Planned Manpower | 132 | 228 | 236 | 236 | 228 | 236 | 228 | 236 | 236 | 209 | 236 | 228 | 379 | 379 | 379 | 232 | 232 | 232 | 261 | 99 | 99 | 70 | 32 | 32
Actual Manpower | 2017-05-01: 86; 2017-06-01: 148; 2017-07-01: 153; 2017-08-01: 153; 2017-09-01: 148; 2017-10-01: 153; 2017-11-01: 148; 2017-12-01: 153; 2018-01-01: 153; 2018-02-01: 178; 2018-03-01: 201; 2018-04-01: 194; 2018-05-01: 322
Cum. Monthly Planned Manpower | 187 | 415 | 651 | 887 | 1115 | 1351 | 1579 | 1815 | 2051 | 2260 | 2496 | 2724 | 3103 | 3482 | 3861 | 4093 | 4325 | 4557 | 4818 | 4917 | 5016 | 5086 | 5118 | 5150
Cum. Monthly Actual Manpower | 2017-05-01: 187; 2017-06-01: 335; 2017-07-01: 488; 2017-08-01: 641; 2017-09-01: 789; 2017-10-01: 942; 2017-11-01: 1090; 2017-12-01: 1243; 2018-01-01: 1396; 2018-02-01: 1574; 2018-03-01: 1775; 2018-04-01: 1969; 2018-05-01: 2291
TOTAL: 5150

## J
Current % Progress Vs Previous % Progress
|  | Current % Progress | Previous % Progress | Periods Ago |  |  | Contract | 23675265
|  | 2018-05-01 | 2018-04-01 | 2018-03-01
| Cum.Plan | 78.5% | 72.85% | 59.03% |  | 2018-03-01 | 2018-04-01 | Current Total
| Cum.Actual | 45.48% | 39.83% | 35.81% | 33.02% | 8642465.64 | 786634.23 | 9429099.87
| Plan | 5.655% | 13.82% | 0% |  | 36.5% | 3.323% | 39.83%
| Actual | 5.655% | 4.013% | 0%
| Variance | -1.11e-14% | -9.808% | 0%
FORECAST

## K - CASH FLOW S-Curve
Al Wukair Villa
Project Start : |  |  |  | 2017-05-18
Project Finish : |  |  |  | 2019-01-14
Project Value : |  |  | 23675265
REVENUE SCHEDULE | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01
Monthly Planned Values, QAR | 56624.2203 | 117967.6355 | 193127.6788 | 255390.8038 | 376999.6856 | 523030.7075 | 676877.5136 | 992887.8547 | 1616310.2999 | 4298044.0028 | 4867489.4531 | 3271981.9033 | 1338902.1959 | 1095465.433 | 826935.9811 | 689973.7606 | 676583.9846 | 576847.9334 | 471966.491 | 413521.6039 | 338335.8577 | [7 empty] | 23675265
Monthly Actual Values, QAR | 2017-05-01: 175114.8638; 2017-06-01: 364825.36; 2017-07-01: 394010.6748; 2017-08-01: 394010.6748; 2017-09-01: 364825.36; 2017-10-01: 468399.0144; 2017-11-01: 847861.6576; 2017-12-01: 1353915.9757; 2018-01-01: 1166478.4235; 2018-02-01: 1085482.481; 2018-03-01: 1864165.1249; 2018-04-01: 950010.2594; 2018-05-01: 1338902.1959 | 10768002.0659
Monthly Remaining Early Values, QAR | 2018-06-01: 168558.6204; 2018-07-01: 1147374.7678; 2018-08-01: 2039280.2462; 2018-09-01: 2872256.3978; 2018-10-01: 2172981.7595; 2018-11-01: 1822036.0733; 2018-12-01: 1447215.8713; 2019-01-01: 739109.5525; 2019-02-01: 372772.2054; 2019-03-01: 30673.7993; 2019-04-01: 20449.1996; 2019-05-01: 33229.868; 2019-06-01: 22153.2454; 2019-07-01: 11502.7966; 2019-08-01: 7668.5311 | 12907262.9341 | 23675265
Monthly Remaining Late Values, QAR | 2018-06-01: 30814.1962; 2018-07-01: 76525.5227; 2018-08-01: 385954.9983; 2018-09-01: 825905.3906; 2018-10-01: 1670481.0783; 2018-11-01: 2265649.1349; 2018-12-01: 2947493.3238; 2019-01-01: 1575955.2855; 2019-02-01: 1050636.857; 2019-03-01: 622866.3298; 2019-04-01: 415244.2198; 2019-05-01: 473869.7868; 2019-06-01: 315913.1912; 2019-07-01: 149972.1715; 2019-08-01: 99981.4476 | 12907262.9341 | 23675265
Cum. Monthly Planned Values, QAR | 56624.2203 | 174591.8558 | 367719.5346 | 623110.3384 | 1000110.024 | 1523140.7314 | 2200018.2451 | 3192906.0997 | 4809216.3996 | 9107260.4024 | 13974749.8556 | 17246731.7589 | 18585633.9547 | 19681099.3877 | 20508035.3689 | 21198009.1294 | 21874593.114 | 22451441.0474 | 22923407.5384 | 23336929.1423 | 23675265
Cum. Monthly Actual Values, QAR | 2017-05-01: 175114.8638; 2017-06-01: 539940.2238; 2017-07-01: 933950.8986; 2017-08-01: 1327961.5734; 2017-09-01: 1692786.9335; 2017-10-01: 2161185.9478; 2017-11-01: 3009047.6055; 2017-12-01: 4362963.5812; 2018-01-01: 5529442.0046; 2018-02-01: 6614924.4857; 2018-03-01: 8479089.6106; 2018-04-01: 9429099.87; 2018-05-01: 10768002.0659
Cum. Monthly Remaining Early Values, QAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10768002.0659 | 10936560.6862 | 12083935.454 | 14123215.7003 | 16995472.0981 | 19168453.8575 | 20990489.9308 | 22437705.8021 | 23176815.3546 | 23549587.56 | 23580261.3594 | 23600710.5589 | 23633940.4269 | 23656093.6723 | 23667596.4689 | 23675265
Cum. Monthly Remaining Late Values, QAR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10768002.0659 | 10798816.2621 | 10875341.7848 | 11261296.7831 | 12087202.1737 | 13757683.2521 | 16023332.3869 | 18970825.7108 | 20546780.9963 | 21597417.8533 | 22220284.183 | 22635528.4029 | 23109398.1897 | 23425311.3809 | 23575283.5524 | 23675265
% REVENUE SCHEDULE | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01
Monthly Planned Values, % | 0.2392% | 0.4983% | 0.8157% | 1.079% | 1.592% | 2.209% | 2.859% | 4.194% | 6.827% | 18.15% | 20.56% | 13.82% | 5.655% | 4.627% | 3.493% | 2.914% | 2.858% | 2.437% | 1.994% | 1.747% | 1.429%
Monthly Actual Values, % | 2017-05-01: 0.7397%; 2017-06-01: 1.541%; 2017-07-01: 1.664%; 2017-08-01: 1.664%; 2017-09-01: 1.541%; 2017-10-01: 1.978%; 2017-11-01: 3.581%; 2017-12-01: 5.719%; 2018-01-01: 4.927%; 2018-02-01: 4.585%; 2018-03-01: 7.874%; 2018-04-01: 4.013%; 2018-05-01: 5.655%
Monthly Remaining Early Values, % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.712% | 4.846% | 8.614% | 12.13% | 9.178% | 7.696% | 6.113% | 3.122% | 1.575% | 0.1296% | 0.08637% | 0.1404% | 0.09357% | 0.04859% | 0.03239%
Monthly Remaining Late Values, % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1302% | 0.3232% | 1.63% | 3.488% | 7.056% | 9.57% | 12.45% | 6.657% | 4.438% | 2.631% | 1.754% | 2.002% | 1.334% | 0.6335% | 0.4223%
Cum. Monthly Planned Values, % | 0.2392% | 0.7374% | 1.553% | 2.632% | 4.224% | 6.433% | 9.292% | 13.49% | 20.31% | 38.47% | 59.03% | 72.85% | 78.5% | 83.13% | 86.62% | 89.54% | 92.39% | 94.83% | 96.82% | 98.57% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cum. Monthly Actual Values, % | 0.7397% | 2.281% | 3.945% | 5.609% | 7.15% | 9.128% | 12.71% | 18.43% | 23.36% | 27.94% | 35.81% | 39.83% | 45.48% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Cum. Monthly Remaining Early Values, % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 45.48% | 46.19% | 51.04% | 59.65% | 71.79% | 80.96% | 88.66% | 94.77% | 97.89% | 99.47% | 99.6% | 99.69% | 99.83% | 99.92% | 99.97% | 100%
Cum. Monthly Remaining Late Values, % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 45.48% | 45.61% | 45.94% | 47.57% | 51.05% | 58.11% | 67.68% | 80.13% | 86.79% | 91.22% | 93.85% | 95.61% | 97.61% | 98.94% | 99.58% | 100%
| 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [10 empty] | 0%
| 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [10 empty] | 0%
`
Monthly Value

## K (hidden)
Project Cost % Progress | 0.12 | 0.251 | 0.3156 | 0.555 | 0.7845 | 1.1256 | 1.4173 | 1.4226 | 1.5584 |  | 0.9 | 0.3 | 8.75
Project Value: | 0.013714 | 0.028686 | 0.036069 | 0.063429 | 0.089657 | 0.12864 | 0.16198 | 0.16258 | 0.1781 |  | 0.10286 | 0.034286 | 1
23675265
| 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01
Monthly Planned Value (BCWS), PV | 0.2392% | 0.4983% | 0.8157% | 1.079% | 1.592% | 2.209% | 2.859% | 4.194% | 6.827% | 18.15% | 20.56% | 13.82% | 5.655% | 4.627% | 3.493% | 2.914% | 2.858% | 2.437% | 1.994% | 1.747% | 1.429%
Monthly Earned Value (BCWP), EV | 2017-05-01: 0.7%; 2017-06-01: 1.45%; 2017-07-01: 1.57%; 2017-08-01: 1.57%; 2017-09-01: 1.45%; 2017-10-01: 1.86%; 2017-11-01: 3.37%; 2017-12-01: 5.38%; 2018-01-01: 4.63%; 2018-02-01: 4.31%; 2018-03-01: 7.41%; 2018-04-01: 3.77%; 2018-05-01: 2.36%
Monthly Actual Value (GVWD), GVWD | 2017-05-01: 0%; 2017-06-01: 0%; 2017-07-01: 0%; 2017-08-01: 0%; 2017-09-01: 0%; 2017-10-01: 0%; 2017-11-01: 0%; 2017-12-01: 36.5%; 2018-01-01: 3.32%; 2018-02-01: 8.98%
Cum. Monthly Planned Value (BCWS), PV | 2017-05-01: 0.2392%; 2017-06-01: 0.7374%; 2017-07-01: 1.553%; 2017-08-01: 2.632%; 2017-09-01: 4.224%; 2017-10-01: 6.433%; 2017-11-01: 9.292%; 2017-12-01: 13.49%; 2018-01-01: 20.31%; 2018-02-01: 38.47%
Cum. Monthly Earned Value (BCWP), EV | 2017-05-01: 0.7%; 2017-06-01: 2.15%; 2017-07-01: 3.72%; 2017-08-01: 5.29%; 2017-09-01: 6.74%; 2017-10-01: 8.6%; 2017-11-01: 11.97%; 2017-12-01: 17.35%; 2018-01-01: 21.98%; 2018-02-01: 26.29%
Cum. Monthly Actual Value (GVWD), GVWD | 2017-05-01: 0%; 2017-06-01: 0%; 2017-07-01: 0%; 2017-08-01: 0%; 2017-09-01: 0%; 2017-10-01: 0%; 2017-11-01: 0%; 2017-12-01: 36.5%; 2018-01-01: 39.82%; 2018-02-01: 48.8%
Cum. Schedule Variance (EV-PV) | 2017-05-01: 0.4608%; 2017-06-01: 1.413%; 2017-07-01: 2.167%; 2017-08-01: 2.658%; 2017-09-01: 2.516%; 2017-10-01: 2.167%; 2017-11-01: 2.678%; 2017-12-01: 3.864%; 2018-01-01: 1.667%; 2018-02-01: -12.18%
Cum. Cost Variance (EV- GVWD) | 2017-05-01: 0.7%; 2017-06-01: 2.15%; 2017-07-01: 3.72%; 2017-08-01: 5.29%; 2017-09-01: 6.74%; 2017-10-01: 8.6%; 2017-11-01: 11.97%; 2017-12-01: -19.15%; 2018-01-01: -17.84%; 2018-02-01: -22.51%
Schedule Performance Index (SPI) (EV/PV) | 2017-05-01: 2.9268; 2017-06-01: 2.9155; 2017-07-01: 2.3951; 2017-08-01: 2.01; 2017-09-01: 1.5955; 2017-10-01: 1.3368; 2017-11-01: 1.2881; 2017-12-01: 1.2865; 2018-01-01: 1.0821; 2018-02-01: 0.68344
Cost Performance Index (CPI) (EV/GVWD) | 2017-05-01: #DIV/0!; 2017-06-01: #DIV/0!; 2017-07-01: #DIV/0!; 2017-08-01: #DIV/0!; 2017-09-01: #DIV/0!; 2017-10-01: #DIV/0!; 2017-11-01: #DIV/0!; 2017-12-01: 0.47534; 2018-01-01: 0.55198; 2018-02-01: 0.53873

## Ix (hidden)
| Site Staff Schedule | 0.12 | 0.251 | 0.3156 | 0.555 | 0.7845 | 1.1256 | 1.4173 | 1.4226 | 1.5584 | 1.25 | 0.9 | 0.3 | 10
|  | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01
| Monthly Planned Site Staff | 12 | 18 | 21 | 22 | 26 | 26 | 26 | 26 | 22 | 21 | 16 | 4
| Monthly Actual Site Staff | 9 | 13 | 19 | 22 | 22 | 22 | 24 | 24 | 19 | 19 | 16
| Cum. Monthly Planned Site Staff | 12 | 30 | 51 | 73 | 99 | 125 | 151 | 177 | 199 | 220 | 236 | 240
| Cum. Monthly Actual Site Staff | 9 | 22 | 41 | 63 | 85 | 107 | 131 | 155 | 174 | 193 | 209
| Project Director - Planned | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Project Director - Actual | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Project Manager - Planned | bar: 2017-01-01 to 2017-12-01
| Project Manager - Actual | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Construction Manager - Planned | bar: 2017-01-01 to 2017-12-01
| Construction Manager - Actual | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Technical Manager - Planned | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Technical Manager - Actual | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Technical Coordinator - Planned | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Technical Coordinator - Actual | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Architect - Planned | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Architect - Actual | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Technical Engineer - Planned | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Technical Engineer - Actual | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| CAD Operator - Planned | 0 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 0
| CAD Operator - Actual | 0 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 1 | 1 | 1 | 0
| Project Engineer - Planned | 1 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 0
| Project Engineer - Actual | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 1 | 1 | 1 | 0
| Document Controller - Planned | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Document Controller - Actual | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Civil Supervisor - Planned | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Civil Supervisor - Actual | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Mechanical Supervisor - Planned | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Mechanical Supervisor - Actual | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Electrical Supervisor - Planned | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Electrical Supervisor - Actual | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Surveyor - Planned | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Surveyor - Actual | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Time keeper - Planned | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Time keeper - Actual | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Store keeper - Planned | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
| Store keeper - Actual | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
| QA/QC Engineer - Planned | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| QA/QC Engineer - Actual | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| HSE Officer - Planned | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| HSE Officer - Actual | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
This Chart
S.N. | SUPERVISION TEAM | 2017-02-01: HEAD-COUNT; 2017-04-01: REMARKS
1 | Project Director
2 | Project Manager
3 | Construction Manager
4 | Technical Manager
5 | Technical Coordinator
6 | Architect
7 | Technical Engineer
8 | CAD Operator
9 | Project Engineer
10 | Document Controller
11 | Civil Supervisor
12 | Mechanical Supervisor
13 | Electrical Supervisor
14 | Surveyor
15 | Time keeper
16 | Store keeper
17 | QA/QC Engineer
18 | HSE Officer

## Kx (hidden)
| Equipment & Machineries Schedule | 0.12 | 0.251 | 0.3156 | 0.555 | 0.7845 | 1.1256 | 1.4173 | 1.4226 | 1.5584 | 1.25 | 0.9 | 0.3 | 10
|  | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01
| Monthly Planned Equipment | 4 | 16 | 17 | 26 | 27 | 24 | 24 | 22 | 11 | 8 | 6 | 3
| Monthly Actual Equipment | 5 | 12 | 22 | 24 | 28 | 29 | 27 | 23 | 16 | 10 | 6
| Cum. Monthly Planned Equipment | 4 | 20 | 37 | 63 | 90 | 114 | 138 | 160 | 171 | 179 | 185 | 188
| Cum. Monthly Actual Equipment | 5 | 17 | 39 | 63 | 91 | 120 | 147 | 170 | 186 | 196 | 202
| Boom Truck - Planned | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Boom Truck - Actual | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Generators (Fix) - Planned | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1
| Generators (Fix) - Actual | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 0
| Generators (portable) - Planned | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1
| Generators (portable) - Actual | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 0
| Welding Machine - Planned | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
| Welding Machine - Actual | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 0
| Bobcat - Planned | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Bobcat - Actual | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 0
| Compactor - Planned | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 2 | 1 | 1 | 1
| Compactor - Actual | 1 | 1 | 1 | 2 | 3 | 1 | 0 | 0 | 3 | 2 | 1 | 0
| Concrete Vibrator - Planned | 0 | 2 | 2 | 4 | 4 | 3 | 3 | 2 | 0 | 0 | 0 | 0
| Concrete Vibrator - Actual | 0 | 2 | 3 | 4 | 4 | 6 | 4 | 1 | 0 | 0 | 0 | 0
| Bar Bender - Planned | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Bar Bender - Actual | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
| Bar Cutter - Planned | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Bar Cutter - Actual | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
| Floater - Planned | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
| Floater - Actual | 0 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0
| Forklift - Planned | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Forklift - Actual | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 0
| Air Compressors - Planned | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Air Compressors - Actual | 1 | 2 | 2 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0
| Trailer - Planned | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Trailer - Actual | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Man Lift - Planned | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Man Lift - Actual | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Loader - Planned | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Loader - Actual | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | 0
| Dumptruck - Planned | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Dumptruck - Actual | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
This Chart
EQUIPMENT & MACHINERIES
S.N. | Macinery & Equipment | 2017-03-01: QTY; 2017-04-01: SUPPLIER; 2017-05-01: REMARKS
1 | Tower Crane
2 | Mobile Crane
3 | Water Tanker
4 | Roller Compactor
5 | Boom Truck
6 | Generators (Fix)
7 | Generators (portable)
8 | Welding Machine
9 | Bobcat
10 | Compactor
11 | Concrete Vibrator
12 | Bar Bender
13 | Bar Cutter
14 | Floater
15 | Forklift
16 | Air Compressors
17 | Trailer
18 | Man Lift
19 | Loader
20 | Dumptruck

## Data
|  |  | Previous week |  |  |  | Current Week | [5 empty] | 2 weeks |  |  |  |  | 4 weeks
|  | %Planned |  | %Actual | % Variance | Project Scope Progress Status | %Planned | %Actual | % Variance |  |  | %Planned |  | %Actual | % Variance |  | %Planned |  | %Actual | % Variance
| 13.82% | 72.85% | 4.013% | 39.83% | -33.02% | Overall Project % Progress | 78.5% | 45.48% | -33.02% |  | 2.314% | 80.82% | 2.314% | 47.8% | -33.02% | 4.627% | 83.13% | 4.627% | 50.11% | -33.02%
8.34% | 1.153% | 66.3% | 0.3347% | 67.12% | 0.818% | PRELIMINARIES | 67.45% | 67.45% | 0% |  | 0.4715% | 67.92% | 0.1369% | 67.59% | -0.3346% | 0.943% | 68.39% | 0.2738% | 67.73% | -0.6692%
0.14% | 0.01935% | 99.98% | 0.005618% | 99.05% | -0.9268% | ENABLING WORKS | 100% | 99.06% | -0.9405% |  | 0.007915% | 100% | 0.002298% | 99.06% | -0.9462% | 0.01583% | 100% | 0.004596% | 99.06% | -0.9518%
38.54% | 5.326% | 84.67% | 1.546% | 76.43% | -8.246% | CIVIL AND STRUCTURAL WORKS | 90% | 77.97% | -12.03% |  | 2.179% | 92.18% | 0.6327% | 78.61% | -13.57% | 4.358% | 94.36% | 1.265% | 79.24% | -15.12%
52.98% | 7.322% | 6.178% | 2.126% | 5.941% | -0.2373% | MEP WORKS | 13.5% | 8.067% | -5.433% |  | 2.995% | 16.5% | 0.8697% | 8.936% | -7.559% | 5.991% | 19.49% | 1.739% | 9.806% | -9.685% | `
0% | 0% | 0% | 0% | 0% | 0% | THERMAL AND MOISTURE PROTECTION | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0% | 0% | 0% | 0% | 0% | 0% | EXTERNAL CIVIL WORKS | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0% | 0% | 0% | 0% | 0% | 0% | SPECIALTIES | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
0% | 0% | 0% | 0% | 0% | 0% | PROVISIONAL SUM | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[7 empty] | Plan | Actual
[6 empty] | Factor | 100% | 100%
[6 empty] | Current Actual | 78.5% | 45.48%
[6 empty] | Remaining Target | 21.5% | 54.52%
[6 empty] | % per week | 1.157% | 1.157% |  | Target next Month |  | 4.627%
[6 empty] | 2 weeks Target | 2.314% | 2.314%
[6 empty] | Prev-Actual | 5.655% | 5.655%
[7 empty] | 2.314% | 2.314%