## Summary of All Issues Found
No. | Section | Issue Description | Assigned to | Status | Date Raised | Comment | Ken's Comment
RCB-01 | Loan Accounts Tab ¦ Export Loan Accounts | Empty Excel file was generated when exporting and Business Unit = All | Andrea | Closed | 2015-09-09 | Bug already fixed
RCB-02 | Loan Accounts Tab ¦ View Upfront Payments for a Loan Account: | The table grid was not displayed if user selected a Loan Account with no Upfront Payments, Trail Payments, Referrers linked to it. An indicator like a display message would be helpful. | Rose | Closed | 2015-09-09 | Document already updated.
RCB-03 | Tax Invoices ¦ View Draft Tax Invoice Detail | Upfront is misspelled as Ufront under Tax Invoices table grid, see http://screencast.com/t/P60fRBK8X | Rose | Closed | 2015-09-09 | Bug already fixed
RCB-04 | Payments ¦ Delete Payment Batch | Unable to Delete a Batch payment under Payments tab, Please see: - http://screencast.com/t/8hqLSGmF | Kim | Closed | 2015-10-09 | Done and Passed
RCB-05 | Tax invoices ¦ Create ABA File | Unable to create an ABA file, an error message shown | Kim | Closed | 2015-10-09 | Done and Passed | Error was occuring because there was no BSB number specified in the ABA File Details in admin section for Hastings Mortgages but I will modify to return a more meaningful error when this occurs
RCB-06 | Tax Invoices ¦ Download existing ABA file (Not processed) | Unable to see Download for ABA File under Tax Invoices | Kim | Closed | 2015-10-09 | Done and Passed | Can't download until an aba file is created
RCB-07 | Tax Invoices ¦ Save an ABA file as processed | Unable to replicate test cases on the document for Save an ABA file as Processed | Kim | Closed | 2015-10-09 | Done and Passed | dependent on creating aba file
RCB-08 | Tax Invoices ¦ Delete an ABA file (Not processed) | Unable to replicate test cases on the document for Delete an ABA File (Not Processed) | Kim | Closed | 2015-10-09 | Done and Passed | dependent on creating aba file
RCB-09 | Tax Invoices ¦ Download an ABA file (Processed) | Unable to replicate test cases on the document for Download an ABA File as Processed | Kim | Closed | 2015-10-09 | Done and Passed | dependent on creating aba file
RCB-10 | Tax invoices ¦ Download Tax Invoices linked to an ABA file (Processed) | Unable to replicate test cases on the document for Download Tax Invoices linked to an ABA File | Kim | Closed | 2015-10-09 | Done and Passed | dependent on creating aba file
RCB-11 | Payments ¦ View Missing Trail Payments for Trail Batch | No record shows after clicking "View Missing Trail Payments" | Rose | Closed | 2015-10-09 | How do we show a record for Missing Trail Payments? | You need to expire some agreements so no trail is created for some accounts and then rerun the payment batch
RCB-12 | Save an ABA file as processed | Pop Up Dialog not showing after clicking save button | Rose | Closed | 2015-10-09 |  | Fixed
RCB-13 | Loan Accounts ¦ Delete a Referrer from a Loan Account: | When user perform a delete, the first referrer in the list will be deleted and you cannot select a referrer to be deleted in the table grid. Also the last step (Step 5) in the document should be "Click Delete button" and not "Click Save button" | Rose | Closed | 2015-09-09 | Document needs to be updated for step 5 | Document updated
RCB-14 | Payments ¦ View Upfront Clawbacks | Viewing Upfront_Clawback filter is not working. Even though the user choose Upfront_Clawback as the selection criteria the table grid still displays all available payment batch and commission type. Please see http://screencast.com/t/yiky51yJ | Rose | Closed | 2015-10-09 | Done and Passed | I tested it on rubik 1 and it worked
RCB-15 | Loan Account ¦ Sync Type | Lender - Remove on Sync Type option under Upload Files | Rose | Closed | 15/9/2015 | Done and Passed | Removed lender sync type
RCB-16 | RCTI Report | RCTI Report does not match with Tax Invoices | Rose | Closed | 15/9/2015 | Done and Passed | There was an underlying issue with a database view that I have rectified
RCB-17 | Payment ¦ Linked to Profile and Agreement | Created New Profile and Agreement does not reflect on existing Payment Batch | Rose | Closed | 15/9/2015 | Done and Passed
RCB-18 | Agreements ¦ Fixed Trail | Export functionality is not working when clicking Export button - Still need to click the View button first before being able to export the Fixed Trail file | KristinaB | Closed | 15/9/2015 |  | The direct export to excel only works where there is complicated selection criteria such as loan account selector for example. To export life trail you need to load it first. I have updated the documentation as well
RCB-19 | Agreements ¦ Create New Agreement | Update 'Start Date' and 'End Date' to display as 'From Settled' and 'To Settled' when creating an agreement | Rose | Closed | 2015-09-16
RCB-20 | Agreements ¦ Create New Agreement | Selecting 'ALL' as Other Party value when Creating an Agreement results to an error message - 'Failed to save an agreement(s)' | Rose | Closed | 2015-09-16 |  | removed all option from list
RCB-21 | Profiles | User able to create a Profile without Profile Name | Rose | Closed | 2015-09-17 |  | Displays a message when profile name is blank
RCB-22 | Profiles | User need to click add button twice to add tier rate - http://screencast.com/t/em40C7HqgE | Kristina | Closed | 2015-09-18 | PASSED | Removed autopostback from tier name text box
RCB-23 | Loan Accounts ¦ Test Data | Test Data must be checked especially the dates. Date Format should be [dd/mm/yyyy] and not [mm/dd/yyyy] system cannot handle different date format. Wrong date format results to empty or null value cell and this also invalidate the processing of payment batch. | Andrea | Closed | 2015-09-18 | Suggest to update document to inform user to validate test data first before importing it to the database to avoid empty or null value cells
RCB-24 | Profiles ¦ Create New Profile | User need to double click the save button when creating Not_Tiered base profile - http://screencast.com/t/Y5Su6Ebsff | Kim | Closed | 2015-09-21 | PASSED | Removed autopostback from rate text box
RCB-25 | Profiles | Unable to delete Profile - http://screencast.com/t/EXQv4GdX | Steph | Closed | 2015-09-21 | FAILED - http://screencast.com/t/95Ysf4raZ | Problem here is cecause of corrupt profile that applies to all loans but previosuly applied to specific product
RCB-26 | Profiles | Created Referrer Profile can’t be viewed. Viewing the referrer list redirects to an Error Page - http://screencast.com/t/6aWfpWilJ7K | Rose | Closed | 2015-09-21 | Done and Passed | Wasn't loading the required profile base types for referrers
RCB-27 | Admin | Misaligned table on Referrer Group - http://screencast.com/t/XIDUPzmBPvcc | Steph | Closed | 2015-09-22 | PASSED
RCB-28 | Admin | Misaligned table on Referrer Persons - http://screencast.com/t/FfdNQeFYFFj | Steph | Closed | 2015-09-22 | PASSED
RCB-29 | Admin | External SystemID value doesn't change even if the selected Referrer Group was changed - http://screencast.com/t/clkd0Ai95W | Steph | Closed | 2015-09-22 | PASSED. Not an issue based on Ken's Comment. | The external system ID relates to the person not the referrer group so its not supposed to change if you change the referrer group
RCB-30 | Admin | User was able to create ABA Details, Brokers, Referrer Group, and Business Unit (http://screencast.com/t/9oIoFMOMz) without any data | Kristina | Closed | 2015-09-22 | PASSED | added validation checks for this
RCB-31 | Admin | Unable to edit Loan Product Type Code - http://screencast.com/t/YPJxEGmBYyPJ | Steph | Closed | 2015-09-22 | PASSED. Not an issue based on Ken's Comment. | this is by design, the loan product type code is the primary key in the database table and you cannot modify the primary key. You will need to delete the loan product type code and the add a new one
RCB-32 | Admin | User can add Empty 'Not Commissionable Reason' - http://screencast.com/t/5onOayor6q3M | Steph | Closed | 2015-09-22 | PASSED | added validation code
RCB-33 | Admin | Unable to edit Reason Code - http://screencast.com/t/hQwQMnxm | Steph | Closed | 2015-09-22 | PASSED. Not an issue based on Ken's Comment. | this is by design, the reason code is the primary key in the database table and you cannot modify the primary key. You will need to delete the reason code and the add a new one
RCB-34 | Admin ¦ ABA Details | Unable to edit Party drop down menu | Kristina | Closed | 2015-09-22 |  | can't change the aba party on an exisitng abad detail record as thre abaparty is the primary key
RCB-35 | Tax Invoices | Sundry Transaction Added' message is added on the page even if the user cancelled the addition of sundry transaction - http://screencast.com/t/FqO45oar5 | Andrea | Closed | 2015-09-22 | PASSED. Not an issue based on Ken's Comment.
RCB-36 | Admin | Unable to create Loan Products (http://screencast.com/t/ZbGhOrTS) | Kristina | Closed | 2015-09-23 | PASSED | was referring to wrong text box
RCB-37 | Admin | User was able to create Brokers, Referrer Group, and Business Unit (http://screencast.com/t/JT1N5hCkc) without any data to other Mandatory fields | Kristina | Closed | 2015-09-23 | PASSED | will still allow referrer groups and persons to be save without external systemID as they may only use commission system to keep track of referrers
RCB-38 | Tax Invoices ¦ Export Detailed Tax Invoice | User can't export detailed tax invoice of a selected tax invoice (both on draft and final) | Andrea | Closed | 2015-09-23
RCB-39 | Tax Invoices ¦ Add sundry | User can't add sundry transaction even if all fields has values | Andrea | Closed | 2015-09-23 | Error Failed to save sundry transaction to tax invoice Value cannot be null. Parameter name: keyValue
RCB-40 | Profiles ¦ Create New Profile | User able to save non numeric value on 'Base Amount $' and 'Rate %' fields - http://screencast.com/t/G3sjuk3H | Rose | Closed | 2015-09-23 | Done and Passed
RCB-41 | Profiles ¦ Create New Profile | User able to save blank data on all TieredBase != Not_Tiered - http://screencast.com/t/uL8mLL6eWcs | Rose | Closed | 2015-09-23 | Done and Passed
RCB-42 | Profiles ¦ Create New Profile | User able to save higher inputted value on '> Lower Limit Age (Months)' than '<=Upper Limit Loan Balance $' - http://screencast.com/t/PybFFpZN54 | Rose | Closed | 2015-09-23 | Done and Passed
RCB-43 | Tax Invoice ¦ Process a finalized tax invoice | Save button does not trigger a pop-up message informing the user that the tax invoice has been processed | Andrea | Closed | 2015-09-23 |  | Could not reproduce, click the checkbox in the grid to make it final and then click save
RCB-44 | Profiles (All Fields) | Inappropriate Error message when exceeding the limit on each field - http://screencast.com/t/zhaksCnGy | Rose | Closed | 2015-09-24 |  | No too worried about this ….low priority
RCB-45 | All Sections | Replace Delete button into Cancel button on all affected areas - http://screencast.com/t/CcA1Rnqf | Rose | Closed | 2015-09-24
RCB-46 | Admin ¦ ABA Details | Delete button should only be visible when table grid is visible under ABA Details | Rose | Closed | 2015-09-24
RCB-47 | All Sections | User able to save invalid date range From & To Settled Date | Rose | Closed | 2015-09-24 |  | fixed on creation of agreements and payment batches
RCB-48 | Payments | Non commissionable reason is not applied once payment batch already created | Steph | Closed | 2015-09-24
RCB-49 | Admin | Update error message when user able to add duplicate non commissionable reason | Steph | Closed | 2015-09-24
RCB-50 | Payments | Missing error message when inputting invalid date range when viewing batch payment | Rose | Closed | 2015-09-25 |  | This will not cause any problems, the selection just won't return anything
RCB-51 | Admin | Generic Error page was displayed once user view ABA file with deleted Business Unit. >> http://screencast.com/t/sWXtkfNcTfeU | Steph | Closed | 2015-09-25 |  | This occurred because a business unit was partially deleted. The party record linked to it should have also been deleted. Have added extra validation to deletion of business units
RCB-52 | Loan Accounts | Cannot Remove Non Commissionable Reason - http://screencast.com/t/1ZOCNL2lGPhT | Steph | Closed | 2015-09-28 | PASSED. http://screencast.com/t/4IewoDqkPJ
RCB-53 | Profiles | Profile Based % Of' has only shows Loan Amount option - http://screencast.com/t/ODAmnvdKrs | Steph | Closed | 2015-09-28 | PASSED. Not an issue based on Ken's Comment. | the selected commission type changes the available profile base
RCB-54 | Loan Accounts | Client data with Date Closed should not included on the table grid when selecting Commissionable status - http://screencast.com/t/yR6c9wtGo | Steph | Closed | 2015-09-28 | PASSED. http://screencast.com/t/B0FNASroDlI
RCB-55 | Profiles | Modified By User' is not updating when other user is modifying the system except for 'MyStateAdmin' - http://screencast.com/t/kaDdgyfRZ5 | Rose | Closed | 2015-09-28 |  | Make sure you click logout between users . I tested it and seemed to work
RCB-56 | Profiles | After updating profile type as Referrer, it reverts back all changes made on a specific profile - http://screencast.com/t/b55knhMiqlG | Rose | Closed | 2015-09-28
RCB-57 | Profiles | Change Profile Type as Referrer does not take effect - http://screencast.com/t/b55knhMiqlG | Rose | Closed | 2015-09-28
RCB-58 | Profiles | Generic Error page shown when user update profile type - http://screencast.com/t/bNruq4c44BL | Kristina | Closed | 2015-09-28 |  | that was an issue with am upfront agreement being saved with a profile base of loan balance. Fixed UI to prevent the creation of this.
RCB-59 | Payments | When creating new batch payment and failed to create it, an unnecessary data grid shown - http://screencast.com/t/SNU73wuaZTU | Steph | Closed | 2015-09-28 | PASSED. http://screencast.com/t/UNjCL7R0Oq
RCB-60 | Loan Accounts | Brokers should have all data shown on its dropdown menu - http://screencast.com/t/lnf9Spn8dYJ | Kristina | Closed | 2015-09-28
RCB-61 | Admin | Business Unit added under Admin does not update in real time when viewing it under Loan Accounts - http://screencast.com/t/h6AgBkpNcb9h | Rose | Closed
RCB-62 | Sync Data | When all imported files are already finalized, the table grid still shown with Sync details - http://screencast.com/t/fcHTxceUpyj | Rose | Non issue | 2015-09-28 | PASSED. Not an issue based on Ken's Comment. | I want this to stay in grid so they can see the finalize change
RCB-63 | Profiles | Generic Error page shown when user view profile with Loan_Age as TieredBase - http://screencast.com/t/pcoiBP6k | Rose | Closed | 2015-09-29
RCB-64 | Profiles | Generic Error page shown when Condition type changed to Specific_Product - http://screencast.com/t/YUKLMjeG | Rose | Closed | 2015-09-29 |  | Was an issue with a database view
RCB-65 | Profiles | Generic Error page shown when changing TieredBase value into Product_LVR_InterestRate - http://screencast.com/t/ZMMIZo8U | Rose | Closed | 2015-09-29
RCB-66 | Profiles | Real time changes should apply on Profiles table - http://screencast.com/t/DzHJiKAIVY8d | Steph | Closed | 2015-09-30 | PASSED. http://screencast.com/t/6nlG5zwfW
RCB-67 | Profiles | Resetting values back to 0 for Base Amount $ and Rate % when creating a new profile - http://screencast.com/t/E1k3zyx6PZ | Rose | Closed | 2015-09-30 | PASSED - http://screencast.com/t/96iz1Xjv7w
RCB-68 | Payments | Set Current Date by default on Process Date field when creating a new batch payment - http://screencast.com/t/3rynxZCS | Rose | Closed | 2015-09-30 | PASSED. http://screencast.com/t/zuOP6YaWS
RCB-69 | Payments | Divide Trail by 12 should be checked by default when creating a batch payment for Trail -http://screencast.com/t/GwR6kMDU6Zs | Rose | Closed | 2015-09-30 | PASSED. http://screencast.com/t/tx8k2TCDv
RCB-70 | Sync Data | Show Current Sync Set should be checked by default - http://screencast.com/t/4JzvWwoS | Rose | Closed | 2015-09-30 | PASSED. http://screencast.com/t/iYgLrDy5yQV
RCB-71 | Payments | Wrong computation on GST amount for Trail Payments - http://screencast.com/t/9k3ipGNQ | Steph | Closed | 2015-09-30 |  | problem with stored procedure
RCB-72 | Loan Accounts | Poor layout on Referrers table grid header - http://screencast.com/t/TBsWFwP2vW | Steph | Closed | 2015-09-30 | PASSED. http://screencast.com/t/83W2rfrw
RCB-73 | Payments | Export button is not working on View Upfront Clawback - http://screencast.com/t/C3g2UVLzJPA | Steph | Closed | 2015-09-30 | PASSED. http://screencast.com/t/IJ3jMLbg1
RCB-74 | Payments | Generic Error page shown when sorting out Client Names under Missing Trail Payments table grid - http://screencast.com/t/quPHYrsL | Steph | Closed | 2015-09-30 | PASSED. http://screencast.com/t/b6gtVCHsXA
RCB-75 | Payments | Under View Trail Payments table grid, Lender Comments shown as Upfront Payment for Referrer Trail Profile - http://screencast.com/t/RBi54BSZAy | Steph | RE-OPENED | 2015-09-30 | FAILED. http://screencast.com/t/qrk9cYdobvw
RCB-76 | Payments | List should be sort based on Clients Name on Missing Upfront/ Trail Payments table. |  | New | 2015-02-10
RCB-77 | Profiles | Created profile as referrer is not being saved and appeared on table grid |  | New | 2015-05-10 | http://screencast.com/t/KW8dW5Ea

## Test Cases Scenarios
Test suite: E2E (Suite ID: 32922)
Added Test Case Scenarios
Section | Title | # of TCS | TFS Status
Tax Invoices |  | 30
Tax Invoices Page
View Draft Tax Invoice Summary
Finalize Draft Tax Invoices
View Final Tax Invoice Summary
View Final Tax Invoice Detail
Download Tax Invoices
Create, Download and Verify ABA File
Save an ABA File as Processed
View Draft Tax Invoices where Creditor Type = "All", Tax Invoice = "All" and View By = "Summary"
View Draft Tax Invoices where Creditor Type = "All", Tax Invoice = "1" and View By = "Summary"
View Draft Tax Invoice where Creditor Type = "All", Tax Invoice = "1" and View By = "Detail"
Export Draft Tax Invoices where Creditor Type = "All", Tax Invoice = "All" and View By = "Summary"
Export Draft Tax Invoices where Creditor Type = "All", Tax Invoice = "1" and View By = "Summary"
Export Draft Tax Invoice where Creditor Type = "All", Tax Invoice = "1" and View By = "Detail"
Download PDF version of Draft Tax Invoices where Creditor Type = "All", Tax Invoice = "All" and View By = "Summary"
Download PDF version of Draft Tax Invoice where Creditor Type = "All", Tax Invoice = "1" and View By = "Summary"
Finalized Draft Tax Invoice where Tax Invoice = "1"
View Final Tax Invoices where Creditor Type = "All", Tax Invoice = "All" and View By = "Summary"
View Final Tax Invoices where Creditor Type = "All", Tax Invoice = "All" and View By = "Summary"
View Final Tax Invoices where Creditor Type = "All", Tax Invoice = "1" and View By = "Summary"
View Final Tax Invoices where Creditor Type = "All", Tax Invoice = "1" and View By = "Detail"
Export Final Tax Invoices where Creditor Type = "All", Tax Invoice = "All" and View By = "Summary"
Export Final Tax Invoices where Creditor Type = "All", Tax Invoice = "1" and View By = "Summary"
Export Final Tax Invoices where Creditor Type = "All", Tax Invoice = "1" and View By = "Detail"
Download PDF version of Final Tax Invoice where Creditor Type = "All", Tax Invoice = "All" and View By = "Summary"
Download PDF version of Final Tax Invoice where Creditor Type = "All", Tax Invoice = "1" and View By = "Summary"
Create New ABA File on finalized tax invoice where Tax Invoice = "1"
Process a finalized tax invoice with an ABA File = "Mortgage Options [23/09/2015]"
View Paid Tax Invoices where Creditor Type = "All", Tax Invoice = "All", View By = "Summary" and ABA File = "All"
Export Paid Tax Invoices where Creditor Type = "All", Tax Invoice = "All" and View By = "Summary" and ABA File = "All"
Export Paid Tax Invoices where Creditor Type = "All", Tax Invoice = "All" and View By = "Summary" and ABA File = "Mortage Options [23/09/2015]"
Transactions |  | 8
View Final Payment Transactions - All
View Final Payment Transactions - Upfront
View Final Payment Transactions - Trail
View Final Payment Transactions - UpFront_Clawback
View Draft Payment Transactions - All
View Draft Payment Transactions - Upfront
View Draft Payment Transactions - Trail
View Draft Payment Transactions - Upfront Clawback
RCTI Reports |  | 2
Export to PDF on RCTI Report
Export to Excel on RCTI Report
Sync |  | 9
Sync uploads
Sync Data Page
Upload Files
Import Files
Sanity Checj of Files to be uploaded
Verify Non Commissionable Codes and Enter new codes
Verify uploaded Data
Upload Files and Verify Data Sync and Finalize
Upload Files with Invalid Data
Profiles |  | 24
Profile Page
View profiles
Create New profile
Deleted a file that is not yet Sync
Create New Upfront Profiles and New Upfront Agreements and filter Upfront Payment Batches
Create New Trail Profiles and New Trail Agreements and then filter Trail Payment Batches
MyState Upfront : Create Profile where Product Type is Mortgage - (0.55%)
MyState Upfront : Create Profile where Product Type is Commercial - (0.40%
MyState Upfront : Create Profile where Product Type is Personal - (0.50%)
MyState Upfront : Create Profile where Tiered Base = LVR < or > 81% - (0.88% / 0.55%)
MyState Clawback : Create Profile where Tiered Base = Loan_Age
MyState Trail : Create Profile where Product Type = All Loans and Tiered Based = Not_Tiered
MyState Trail : Create Profile where Product Type = Secured Overdraft and Tiered Based = Not_Tiered
MyState Ballast - Upfront: Create Profile where Tiered Base = Product_LVR_InterestRate (0.770%)
MyState Ballast - Trail: Create Profile where Tiered Base = Product_LVR_InterestRate (0.275%)
MyState Rock - Upfront: Create Profile where Product Type = Mortgage and Tiered Base = LVR < or > 81% (0.88% / 0.605%)
MyState Rock - Upfront: Create Profile where Product Type = Commercial and Tiered Base = LVR < or > 81% (0.88% / 0.605%)
MyState Rock - Trail: Create Profile where Product Type = Commercial and Tiered Base = Loan_Age (0.495%)
MyState Rock - Trail: Create Profile where Product Type = Commercial and Tiered Base = Loan_Age with 4 Years Increase Rate (0.70%)
MyState Rock - Trail: Create Profile where Product Type = Mortgage and Tiered Base = Loan_Age (0.495%)
MyState Rock - Trail: Create Profile where Product Type = Mortgage and Tiered Base = Loan_Age with 4 Years Increase Rate (0.70%)
MyState Referrer - Upfront: Create Profile where Product Type = All and Tiered Base = Not_Tiered (0.25%)
MyState Referrer - Trail: Create Profile where Product Type = All and Tiered Base = Not_Tiered (0.15%)
MyState Referrer - Upfront Clawback: Create Profile where Product Type = All and Tiered Base = Loan Age
Agreements |  | 21
Agreements Page
Create New Agreement
Verify changes of Agreements on Payment Batch
Create Agreement for 'Mortgage 0.55%' Profile
Create Agreement for 'Commercial 0.40% - Upfront' Profile
Create Agreement for 'Personal 0.50% - Upfront' Profile
Create Agreement for 'LVR - Upfront' Profile
Create Agreement for 'Upfront Clawback' Profile
Create Agreement for 'Trail 0.25%' Profile
Create Agreement for 'Trail 0.15%' Profile
Create Agreement for 'Ballast Loan - Upfront' Profile
Create Agreement for 'Ballast Loan - Trail' Profile
Create Agreement for 'Mortgage LVR - Upfront' Profile
Create Agreement for 'Commercial LVR - Upfront' Profile
Create Agreement for 'Commercial Trail - Less than 4yrs ' Profile
Create Agreement for 'Commercial Trail- Loan Age 4yrs' Profile
Create Agreement for 'Mortgage Trail - Less than 4yrs ' Profile
Create Agreement for 'Mortgage Trail- Loan Age 4yrs' Profile
Create Agreement for 'Referrer Upfront - 0.25%' Profile
Create Agreement for 'Referrer Trail - 0.15%' Profile
Create Agreement for 'Referrer Upfront Clawback - 0.15%' Profile
Payments |  | 14
Payment Page
View Payment Batches
Create New Payment Batch
Run Payment Batch
View Payments for Upfront and Trail Batches
Create Upfront Payment Batch for all Upfront Profiles and Agreements from date settled (15/15/1998) to (21/11/2012)
Create Upfront Clawback Payment Batch for all Upfront Clawback Profiles and Agreements from date closed (27/7/2009) to (29/8/2013)
Create Trail Payment Batch for all Trail Profiles and Agreements
Run 'Upfront Payment Batch' for all Upfront Profiles and Agreements from date settled (15/15/1998) to (21/11/2012)
Run 'Upfront Clawback Payment Batch' for all Upfront Clawback Profiles and Agreements from date closed (27/7/2009) to (29/8/2013)
Payments - Run 'Trail Payment Batch' for all Trail Profiles and Agreements
View Upfront Payments, Total Upfront Payout Per Loan Account and Missing Upfront Payments for 'Upfront Payment Batch'
View Trail Payments, Total Trail Payout Per Loan Account and Missing Trail Payments for 'Trail Payment Batch'
View Upfront Clawbacks for 'Upfront Clawback Payment Batch'
Admin |  | 7
Edit an existing Loan Product’s loan Product Type after importing Loan Products data
Create Loan Product Type and assign to an existing Loan Product after importing Loan Products data
Upload ABA File
Create Loan Product Types
Create Loan Products
Create and Apply Non Commissionable Reason
Create and Apply Non Commissionable Reason with existing Payment Batch
Total Test Cases |  | 115

## Action
No. | Description | Work | Date
1 | Loan Accounts Tab ¦ Export Loan Accounts: Empty Excel file was generated when exporting and Business Unit = All | Code Fix applied | 2015-10-09
2 | Loan Accounts Tab ¦ View Upfront Payments for a Loan Account: The table grid was not displayed if user selected a Loan Account with no Upfront Payments, Trail Payments, Referrers linked to it. An indicator like a display message would be helpful. | Updated the document | 2015-10-09
3 | Loan Accounts ¦ Delete a Referrer from a Loan Account: When you perform a delete, the first referrer in the list will be deleted and you cannot select a referrer to be deleted in the table grid. Also the last step (Step 5) in the document should be "Click Delete button" and not "Click Save button" | Code Fix Applied | 2015-10-09
4 | Loan Accounts ¦ Change the Commissionable Status for a Loan Account: Suggestion in step 4, we can say "Select a Non Commissionable Reason from the list" instead of "Select a status from the list" so user can easily identify the field. | Updated the document | 2015-10-09
5 | Profiles ¦ View Profiles: Currently the screenshot in the document looks cropped. Suggestion is to update the Screenshot in the document to show the full Profile details so user can see the expected columns included in the table grid | Updated the document | 2015-10-09
6 | Profiles ¦ View Profiles: Export button functionality under View Profiles tab is not yet in the document | Updated the document | 2015-10-09
7 | Agreements ¦ Edit Existing Agreement: Export button functionality under Edit Existing Agreements is not yet in the document | Updated the document | 2015-10-09
8 | Agreements ¦Fixed Trail Header: Export button functionality under Fixed Trail Header is not yet in the document | Updated the document | 2015-10-09
9 | Tax Invoices ¦ View Draft Tax Invoice Detail Upfront is misspelled as Ufront | Code Fix Applied | 2015-10-09
10 | Payments ¦ Delete Payment Batch Unable to Delete a Batch payment | Code Fix applied | 2015-10-09
11 | Payments ¦ View Payments for Upfront Batch Suggestion in step 5, Instead of using "Click the Upfront Payments header" we can say "Click the View Upfront Payments header" since that is the title of the header. | Updated the document | 2015-10-09
12 | Payments ¦ View Missing Trail Payments for Trail Batch No record shows after clicking "View Missing Trail Payments"
13 | Payments ¦ View Upfront Clawbacks Viewing Upfront_Clawback filter does not work. Even though the user choose Upfront_Clawback as the selection criteria the table grid still displays all available payment batch and commission type.
14 | Tax invoices ¦ Create ABA File Unable to create an ABA file. We are getting an error | No Fix Applied, Not a bug | 2015-10-09
15 | Tax Invoices ¦ Download existing ABA file (Not processed) Unable to see Download for ABA File, is it referring to Download PDF button? | No Fix Applied, Not a bug | 2015-10-09
16 | Tax Invoices ¦ Save an ABA file as processed Tried to follow the steps from the document but unable to replicate in the system | No Fix Applied, Not a bug | 2015-10-09
17 | Tax Invoices ¦ Delete an ABA file (Not processed) Tried to follow the steps from the document but unable to replicate in the system | No Fix Applied, Not a bug | 2015-10-09
18 | Tax Invoices ¦ Download an ABA file (Processed) Tried to follow the steps from the document but unable to replicate in the system | No Fix Applied, Not a bug | 2015-10-09
19 | Tax invoices ¦ Download Tax Invoices linked to an ABA file (Processed) Tried to follow the steps from the document but unable to replicate in the system | No Fix Applied, Not a bug | 2015-10-09
20 | Profiles ¦ Profile Details for other Tiered Base value Add, Update and Delete button functionality under Profiles > Profile Details for other TieredBase value
21 | Agreements ¦ Edit Existing Agreement Date picker not showing when editing existing equipment
22 | Save an ABA file as processed Pop Up Dialog not showing after clicking save button

## Potential Improvement
No. | Section | Improvement Description | Comment | Ken's Comment
RCI-01 | Loan Accounts ¦ Change the Commissionable Status for a Loan Account: | Suggestion in step 4, we can say "Select a Non Commissionable Reason from the list" instead of "Select a status from the list" so user can easily identify the field. | Fixed
RCI-02 | Profiles ¦ View Profiles: | Currently the screenshot in the document looks cropped. Suggestion is to update the Screenshot in the document to show the full Profile details so user can see the expected columns included in the table grid | Fixed
RCI-03 | Profiles ¦ View Profiles: | Export button functionality under View Profiles tab is not yet in the document | Fixed
RCI-04 | Agreements ¦ Edit Existing Agreement: | Export button functionality under Edit Existing Agreements is not yet in the document | Fixed
RCI-05 | Agreements ¦Fixed Trail Header: | Export button functionality under Fixed Trail Header is not yet in the document | Fixed
RCI-06 | Payments ¦ View Payments for Upfront Batch | Suggestion in step 5, Instead of using "Click the Upfront Payments header" we can say "Click the View Upfront Payments header" since that is the title of the header. | Fixed
RCI-07 | Profiles ¦ Profile Details for other Tiered Base value | Add, Update and Delete button functionality under Profiles > Profile Details for other TieredBase value | Open
RCI-08 | Agreements ¦ Edit Existing Agreement: | Date picker not showing when editing existing agreement | Open
RCI-09 | Agreements ¦ View Data Grid | Additional Column in the data grid to show commission type | Fixed
RCI-10 | Agreements ¦ Fixed Trail | Update Document - Remove Step 3 (Enter Selection Criteria) for Export Fixed Trail test case as it does not have any selection drop down field shown in the system. | Fixed
RCI-11 | Sync Data | Update the document to Remove Step 2: "Select the file to import" since selecting a Sync Type will automatically populate Select File value | Fixed
RCI-12 | Sync Data ¦ Import Files | Sync Upload function test case(s) is not yet in the document | Open
RCI-13 | All Pages | Realtime changes should apply on all tables - http://screencast.com/t/oNvUXTRW9
RCI-14 | Payments | Add a Search text field for Payment Batch Name
RCI-15 | Payments | Add a checkbox to show all payment batch
RCI-16 | Payments | By default, payment batch should not be shown on table grid if tax invoice status is final
RCI-17 | All Pages | Update fields to be in gray color when it is not editable
RCI-18 | Payments | Add a placeholder - Edit Controls for Completed Batches or 'Hide' control
RCI-19 | Payments | Add 'Business Unit' column for Missing Upfront Payments table grid
RCI-20 | Profiles | Add 'Used Profile' column to indicate Profiles are already used
RCI-21 | Profiles ¦ Tiered Base | Remove Interest Rate and Product_LVR_InterestRate options under TieredBase drop down menu
RCI-22 | Agreements | Add "All" on Other Party List for Referrer