## June 27th Release v4.12
Requirement | UAT Required | UAT Handover | Date of Deadline | Sign Off | Comments
Suncorp CRS
ELL-163: Suncorp CRS [Story] new fields to capture CRS details for Person Applicants | YES | YES |  | YES
ELL-164: Suncorp CRS [Story] update existing Suncorp Short Form “ADDITIONAL REQUIREMENTS” session to print updates as per Person Applicant GUI updates | YES | YES |  | YES
ELL-165: Suncorp CRS [Story] new fields to capture CRS details for Company Applicants | YES | YES |  | YES
ELL-167: Suncorp CRS [Story] new fields to capture CRS details for person and company applicants acting on behalf of a Trust | YES | YES |  | YES
ELL-170: Suncorp CRS [Story] add 2 static PDF's into the printing options | YES | YES |  | YES
Macquarie CRS
ELL-115: Macquarie CRS [Story] Add CRS Tax details for Person Applicants | YES | YES
ELL-116: Macquarie CRS [Story] Add CRS Tax details for Company Applicants | YES | YES
ELL-137: Macquarie CRS [Story] Add CRS Tax details for Non-Applicants Company Beneficial Owners and Power of Attorney | YES | YES
ELL-118: Macquarie CRS [Story] Reversed Mortgage, Aged Care and SMSF are out of scope for CRS information | NO | N/A |  | N/A | For tracking purpose only
ELL-145: Macquarie CRS [Story] E-lodge Support Form document update | YES | YES
ELL-178: (UAT Defect) ARMA-1742 - Application Summary - Text "TempId" is being displayed under ForeignTaxResidencyRecords
ELL-183: (UAT Defect) ARMA-1763 Validation error when adding new parties to a Company loan
STG PDP
ELL-124: ELODGELEND-65 [Story] Removal of the interest rate column in the Long Form | YES | YES |  | YES
ELL-123: ELODGELEND-65 [Story] Removal of the monthly repayment column in the Short Form and new Footer | YES | YES |  | YES
ELL-122: ELODGELEND-65 [Story] Update XML Output of @ResidentInAustralia | YES | YES |  | YES
ELL-121: ELODGELEND-65 [Story] Update XML Output of Person Current Residential Address when Country is not Australia | YES | YES |  | YES
BAU Backlog
ELB-733: Generic Cabinet - Cabinet not enabled by default | NO | N/A |  | N/A
ELL-185: ING CRS Project | YES | YES
ELL-126: Westpac - Removal of Products from Sale | YES | YES
ELL-104: Macquarie - New validation rule for Repayment Type field | YES | YES
ELL-105: Macquarie - Do not allow capture of security address on pre-approval loans | YES | YES
ELL-106: Macquarie - [ARMA-1258] Update Rubik phone number validation rules | YES | YES
ELL-141: June Release - Reduce Superfund max IO Period | YES | YES |  | YES
ELL-142: NAB - Static Form Update - Change Home Loan | NO | N/A |  | N/A
ELB-711: Change in Compliance document Credit Proposal | YES | YES
ELB-673: [Story] Sending email to the Broker with the Lender Assigned ID from eLodge+ | TBC | N/A |  | N/A | Out of Scope on PVT
ELB-674: [Story] Sending email to the Broker when application is not accepted by a lender and when application is settled | TBC | N/A |  | N/A | Out of Scope on PVT
ELB-677: First Mortgage St George | NO | N/A |  | N/A
ELL-127: ME Bank - Double up of Living Expenses | NO | N/A |  | N/A
ELB-377: Suncorp Application doube up of liabilities | NO | N/A |  | N/A
ELB-608: (CWL) Suncorp Inconsistent purposes within submission XML causing issues - 3c15161d-8264-425a-a085-a79ca10faad3 - Laila Debes | NO | N/A |  | N/A
ELB-692: (CWL) Suncorp Company party fields are missing the mailing address segment within submission XML - 3c15161d-8264-425a-a085-a79ca10faad3 - Laila Debes | NO | N/A |  | N/A
ELL-176: Urgent STG: Remove Low Doc Product suite effective 1/7/17 | NO | N/A |  | N/A
ELL-172: STG: Remove Seniors Access Products effective 1/7/17 | NO | N/A |  | N/A

## ANZ Release
Requirement | UAT Required | UAT Handover | Sign Off | Comments
ELL-131: ANZ - Disable Interest Only for Simplicity Plus products and update Max IO term to 60 months for eligible products